## Defect_tracker
SI No | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status (Open/Closed) | Remarks
1 | 2026-02-03 | Dataset file not loading correctly during collection | Sprint 1 | Backend Team | Data Issue | Corrected file path and verified dataset format | 2026-02-04 | Closed | Dataset loaded successfully
2 | 2026-02-11 | Missing values and duplicate records found in dataset | Sprint 1 | Backend Team | Data Cleaning | Applied preprocessing and removed duplicates | 2026-02-12 | Closed | Data cleaned properly
3 | 2026-02-18 | Difficulty in understanding feature relationships during EDA | Sprint 2 | Backend Team | Analysis | Used visualization techniques for better understanding | 2026-02-19 | Closed | Features understood clearly
4 | 2026-02-23 | Outliers affecting data analysis results | Sprint 2 | Backend Team | EDA | Detected and handled outliers | 2026-02-24 | Closed | Data improved
5 | 2026-03-07 | Linear Regression giving low accuracy | Sprint 3 | Backend Team | Model Training | Implemented Random Forest for better performance | 2026-03-08 | Closed | Accuracy improved
6 | 2026-03-09 | Model prediction error due to incorrect input format | Sprint 3 | Backend Team | Logic | Corrected input format and prediction logic | 2026-03-10 | Closed | Predictions working
7 | 2026-03-12 | Confusion in evaluation metrics (MAE, RMSE, R²) | Sprint 3 | Backend Team | Evaluation | Calculated and compared all evaluation metrics | 2026-03-13 | Closed | Model evaluated successfully
8 | 2026-03-18 | Frontend form not accepting user input properly | Sprint 4 | Frontend Team | UI Issue | Fixed input validation and form handling | 2026-03-19 | Closed | UI working properly
9 | 2026-03-23 | Error while connecting frontend with backend model | Sprint 4 | Both Team | Integration | Connected API with frontend successfully | 2026-03-24 | Closed | Integration done
10 | 2026-03-29 | Minor errors during final testing phase | Sprint 4 | Both Team | Testing | Performed debugging and fixed issues | 2026-03-30 | Closed | Project completed